## Team Roster
Instance Name | Primary Role | Secondary Role | Port | Status | Description
tech-lead | Technical Lead | Production Readiness Auditor | 4000 | Online | Task assignment, xlsx tracker, design approval, final sign-off, stakeholder communication
architect | Principal Architect | Database Architect | 4001 | Online | Architecture review, schema design, migration planning, module-flows.md documentation
backend | Senior Backend Engineer | DevOps Reviewer | 4002 | Online | Server APIs, business logic, CI/CD, deployment scripts, infrastructure
frontend | Senior Frontend Engineer | QA Lead | 4003 | Online | Next.js pages/components, UI/UX, test writing, test execution

## Module Progress
Module # | Module Name | Completion % | Primary Owner | Status | Priority | Notes
1 | Authentication & User Management | 40% | backend | FINALIZED | High | Remaining: Registration, OTP, Profile Update, Change Password; Flow finalized
2 | Customer Lifecycle Management | 30% | frontend | FINALIZED | High | Needs onboarding flow, profile, address UI; Flow finalized
3 | Plan Management | 20% | backend | FINALIZED | High | CRUD for plans, customer discovery UI; Flow finalized
4 | Subscription Management | 15% | backend | FINALIZED | High | Full lifecycle: pause, resume, cancel, renew; Flow finalized
5 | Address Management | 5% | frontend | FINALIZED | Medium | CRUD + delivery validation; Flow finalized
6 | Wallet Management | 35% | backend | FINALIZED | High | Top-up, refund, ledger; Flow finalized
7 | Security Deposit Management | 15% | backend | FINALIZED | Medium | Deposit refund flow; Flow finalized
8 | Delivery Generation Engine | 80% | backend | FINALIZED | High | Cron automation needed; Flow finalized
9 | Delivery Lifecycle Management | 50% | backend | FINALIZED | High | History, tracking improvements; Flow finalized
10 | Skip Meal Management | 40% | backend | FINALIZED | Medium | Skip history, future schedule; Flow finalized
11 | Driver Management | 45% | backend | FINALIZED | Medium | Driver profile, edit; Flow finalized
12 | Driver Assignment Engine | 0% | backend | FINALIZED | High | Round robin, load distribution; Flow finalized
13 | Driver Dashboard | 50% | frontend | FINALIZED | Medium | Filter, delivery execution; Flow finalized
14 | Delivery Completion Engine | 90% | backend | FINALIZED | High | Minor refinements; Flow finalized
15 | Delivery Reversal Management | 60% | backend | FINALIZED | Medium | Route/UI exposure; Flow finalized
16 | Buffer Meal Management | 70% | backend | FINALIZED | Medium | Cron scheduling; Flow finalized
17 | Tiffin Recovery Management | 65% | backend | In Progress | Medium | Customer-facing view
18 | Customer Dashboard | 65% | frontend | In Progress | High | Browse plans, history
19 | Admin Dashboard | 5% | frontend | Not Started | High | Full admin panels
20 | Notification Management | 0% | frontend | Not Started | Medium | OTP, reminders, alerts
21 | Reports & Analytics | 10% | backend | Not Started | Medium | Financial + delivery reports
22 | Audit & Activity Tracking | 30% | backend | In Progress | Low | Activity logs, wallet audit
23 | Automation & Scheduler Engine | 10% | backend | Not Started | High | Cron jobs, auto-assignment
24 | System Configuration | 25% | backend | Not Started | Low | Configurable rules
25 | Integrations | 0% | backend | Not Started | Medium | Payment gateway, SMS, Email
26 | Security & Compliance | 50% | backend | In Progress | High | Rate limiting, data protection

## Task Tracker
Task ID | Module # | Module Name | Title | Description | Assigned To | Priority | Status | Created Date | Completed Date | Notes
T-001 | 1 | Auth & User Mgmt | Finalize Auth Flow | Analyze and document complete auth workflow in module-flows.md | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-002 | 2 | Customer Lifecycle | Finalize Customer Lifecycle Flow | Document customer onboarding, dashboard, account flows | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-003 | 3 | Plan Management | Finalize Plan Management Flow | Document plan CRUD, discovery, comparison flows | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-004 | 4 | Subscription Mgmt | Finalize Subscription Flow | Document full subscription lifecycle | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-005 | 5 | Address Management | Finalize Address Flow | Document address CRUD and validation | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-006 | 6 | Wallet Management | Finalize Wallet Flow | Document wallet operations, top-up, refund flows | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-007 | 7 | Security Deposit | Finalize Deposit Flow | Document deposit collection and refund flow | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-008 | 8 | Delivery Generation | Finalize Delivery Generation Flow | Document cron-based delivery generation | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-009 | 9 | Delivery Lifecycle | Finalize Delivery Lifecycle Flow | Document delivery status transitions | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-010 | 10 | Skip Meal | Finalize Skip Meal Flow | Document skip request, validation, tracking flows | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-011 | 11 | Driver Management | Finalize Driver Management Flow | Document driver CRUD, activation flows | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-012 | 12 | Driver Assignment | Finalize Driver Assignment Flow | Document assignment engine design | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-013 | 13 | Driver Dashboard | Finalize Driver Dashboard Flow | Document driver dashboard and delivery execution | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-014 | 14 | Delivery Completion | Finalize Delivery Completion Flow | Document delivery validation and financial processing | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-015 | 15 | Delivery Reversal | Finalize Reversal Flow | Document delivery reversal and financial reversal | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-016 | 16 | Buffer Meal | Finalize Buffer Meal Flow | Document buffer activation, tracking, consumption | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-017 | 17 | Tiffin Recovery | Finalize Tiffin Recovery Flow | Document tiffin tracking, debt, recovery flows | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-018 | 18 | Customer Dashboard | Finalize Customer Dashboard Flow | Document dashboard widgets and actions | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-019 | 19 | Admin Dashboard | Finalize Admin Dashboard Flow | Document admin dashboards and KPIs | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-020 | 20 | Notifications | Finalize Notification Flow | Document notification channels and triggers | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-021 | 21 | Reports & Analytics | Finalize Reports Flow | Document all report types and analytics | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-022 | 22 | Audit & Activity | Finalize Audit Flow | Document audit logging requirements | architect | Low | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-023 | 23 | Automation Engine | Finalize Scheduler Flow | Document cron jobs and automation | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-024 | 24 | System Config | Finalize Config Flow | Document system configuration and rules engine | architect | Low | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-025 | 25 | Integrations | Finalize Integrations Flow | Document payment gateway and communication integrations | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-026 | 26 | Security & Compliance | Finalize Security Flow | Document security requirements and compliance | architect | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-027 | 0 | Infrastructure | Configure Backend Production Env | Set NODE_ENV=production on Render, generate strong JWT_SECRET, update CORS_ORIGIN for Vercel domain | backend | High | In Review | 2026-06-16 |  | Code changes done (CORS fix, JWT_SECRET). Render Dashboard env vars pending manual setup by Mohit.
T-028 | 0 | Infrastructure | Configure Frontend Production Env | Update NEXT_PUBLIC_API_URL on Vercel to point to Render backend URL, create .env.local from .env.example | frontend | High | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase
T-029 | 4 | Subscription Management | Finalize Subscription Lifecycle Flow | Analyze and document full subscription lifecycle: pause, resume, cancel, renew, expiry handling, monitoring. Build on existing M2 (Subscription) and M3 (Plans) finalized flows. | architect | High | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. Flow finalized in module-flows.md with deactivated plan renewal handling.
T-030 | 9 | Delivery Lifecycle Management | Finalize Delivery Lifecycle Flow | Analyze and document complete delivery lifecycle: creation, status transitions (PENDING → DISPATCHED → DELIVERED/FAILED/SKIPPED/CANCELLED), tracking, history. Build on already-finalized M8 (Delivery Gen) and M14 (Delivery Completion). | architect | High | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. Low-wallet recheck changed from 5-min poll to pre-slot check.
T-031 | 5 | Address Management | Finalize Address Management Flow | Analyze and document address CRUD operations, delivery validation, service area checks, and default address management for customer subscriptions. | architect | Medium | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. Max addresses changed from 20 to 5.
T-032 | 7 | Security Deposit Management | Finalize Security Deposit Flow | Analyze and document deposit collection, tracking, refund processing, and approval workflow. Integrates with M6 (Wallet) and M14 (Delivery Completion). | architect | Medium | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. Penalty changed to admin-configurable amount (not full deposit). Expiry forfeit clarified.
T-033 | 10 | Skip Meal Management | Finalize Skip Meal Flow | Analyze and document skip request flow, cutoff validation, duplicate prevention, skip tracking, and future skip scheduling. Builds on M8 (Delivery Gen) and M9 (Delivery Lifecycle - skip state machine). | architect | Medium | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. Two skip modes + future scheduling documented.
T-034 | 11 | Driver Management | Finalize Driver Management Flow | Analyze and document driver CRUD, activation/deactivation, profile management, and role handling. Integrates with M12 (Driver Assignment) and M13 (Driver Dashboard). | architect | Medium | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. POLICE_VERIFICATION removed, max_load admin-configurable, service_pincodes dual-set.
T-035 | 12 | Driver Assignment Engine | Finalize Driver Assignment Flow | Analyze and document round-robin assignment logic, driver load distribution, auto-assign and reassign workflows, and assignment history. Builds on finalized M9 (Dispatch) and M11 (Driver Management). | architect | High | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. 3 assignment strategies, eligibility rules, reassignment flow.
T-036 | 13 | Driver Dashboard | Finalize Driver Dashboard Flow | Analyze and document driver dashboard: assigned deliveries view, filtering, delivery execution (arrive/fail/deliver), stats, and profile access. Builds on M9 (Delivery Lifecycle), M11 (Driver Management), M12 (Assignment). | architect | Medium | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. 8 pages, F4 compliance, delivery execution flow.
T-037 | 15 | Delivery Reversal Management | Finalize Delivery Reversal Flow | Analyze and document delivery reversal: reset delivered meals, financial reversal (wallet refund), tiffin reversal, and admin approval workflow. Builds on M14 (Delivery Completion) and M7 (Security Deposit). | architect | Medium | Reviewed | 2026-06-16 | 2026-06-16 | Approved by Mohit. 3 reversal branches, time windows, penalty reversal rules.
T-038 | 16 | Buffer Meal Management | Finalize Buffer Meal Flow | Analyze and document buffer activation, buffer meal tracking/consumption, expiry processing, and integration with M4 (buffer transition) and M8 (buffer delivery generation). | architect | Medium | Reviewed | 2026-06-16 | 2026-06-24 | Batch approved by Mohit — moving to implementation phase

## Activity Log
Timestamp | From Instance | To Instance | Action | Task ID | Outcome
2026-06-08 00:00 | system | all | Team created, relay config updated, tracker initialized | — | Initialized
2026-06-16 19:24 | tech-lead | backend | Assigned T-027: Configure Backend Production Env | T-027 | Pending
2026-06-16 19:24 | tech-lead | frontend | Assigned T-028: Configure Frontend Production Env | T-028 | Pending
2026-06-16 19:24 | tech-lead | repo | Created server/.env.example and client/.env.example | — | Done
2026-06-16 19:30 | frontend | tech-lead | Reported completion of T-027 (backend env config - code changes) | T-027 | In Review
2026-06-16 19:30 | tech-lead | mohit | T-027 code changes done. Mohit needs to set env vars on Render Dashboard and redeploy. | T-027 | Blocked
2026-06-16 19:44 | tech-lead | architect | Assigned T-029: Finalize Subscription Lifecycle Flow (Module 4) | T-029 | Pending
2026-06-16 19:50 | architect | tech-lead | Completed T-029: Subscription Lifecycle Flow documented in module-flows.md | T-029 | Done
2026-06-16 19:50 | tech-lead | mohit | Presenting finalized Module 4 flow for approval | T-029 | In Review
2026-06-16 20:04 | tech-lead | mohit | Mohit approved Module 4 flow after review. Deactivated plan renewal handling updated. | T-029 | Reviewed
2026-06-16 20:19 | tech-lead | architect | Assigned T-030: Finalize Delivery Lifecycle Flow (Module 9) | T-030 | Pending
2026-06-16 20:28 | tech-lead | mohit | Mohit approved Module 9 flow. Low-wallet recheck optimized to 3×/day. | T-030 | Reviewed
2026-06-16 20:29 | tech-lead | architect | Assigned T-031: Finalize Address Management Flow (Module 5) | T-031 | Pending
2026-06-16 20:34 | tech-lead | mohit | Mohit approved Module 5 flow. Max addresses set to 5. | T-031 | Reviewed
2026-06-16 22:44 | tech-lead | architect | Assigned T-032: Finalize Security Deposit Flow (Module 7) | T-032 | Pending
2026-06-16 23:42 | tech-lead | mohit | Mohit approved Module 7 flow. Penalty = admin-configurable amount, deposit stays held separately. | T-032 | Reviewed
2026-06-16 23:44 | tech-lead | architect | Assigned T-033: Finalize Skip Meal Flow (Module 10) | T-033 | Pending
2026-06-17 13:07 | tech-lead | mohit | Mohit approved Module 10 flow. Skip Meal Management finalized. | T-033 | Reviewed
2026-06-17 13:10 | tech-lead | architect | Assigned T-034: Finalize Driver Management Flow (Module 11) | T-034 | Pending
2026-06-17 13:27 | tech-lead | mohit | Mohit approved Module 11 flow. Driver Management finalized. | T-034 | Reviewed
2026-06-17 13:30 | tech-lead | architect | Assigned T-035: Finalize Driver Assignment Flow (Module 12) | T-035 | Pending
2026-06-24 11:52 | tech-lead | mohit | Mohit approved Module 12 flow. Driver Assignment Engine finalized. | T-035 | Reviewed
2026-06-24 12:19 | tech-lead | architect | Assigned T-036: Finalize Driver Dashboard Flow (Module 13) | T-036 | Pending
2026-06-24 14:16 | tech-lead | mohit | Mohit approved Module 13 flow. Driver Dashboard finalized. | T-036 | Reviewed
2026-06-24 15:38 | tech-lead | architect | Assigned T-037: Finalize Delivery Reversal Flow (Module 15) | T-037 | Pending
2026-06-24 15:46 | tech-lead | mohit | Mohit approved Module 15 flow. Delivery Reversal finalized. | T-037 | Reviewed
2026-06-24 15:46 | tech-lead | architect | Assigned T-038: Finalize Buffer Meal Flow (Module 16) | T-038 | Pending
2026-06-24 23:27 | tech-lead | mohit | Mohit approved batch finalization of all 16 modules. Strategy: remaining flows (17-26) on-demand during implementation. Phase 1 (Implementation) begins. | — | Strategy Updated